## Sheet1
Milestone / Deliverable | Owner | Start | Finish | Dependencies/Notes | time axis 2025-09-29 to 2025-12-15
Project engineering document handoff | AES | 2025-10-03 | 2025-10-06 | What can be used from Redonda if anything? | bar: 2025-10-03 to 2025-10-10
AES provide external folder with EPCA exhibits | AES ↔ PRE |  | 2025-10-10 | Populate external drive with necessary exhibits; requires coordination with SMEs. | bar: 2025-10-10
Internal layout modeling (510ac & 550ac) | AES | 2025-10-10 | 2025-10-17 | Modeling required to compare 510ac (2) GSU arrangement to 550ac (3) GSU arrangement. Output feeds layout decision. | bar: 2025-10-10 to 2025-10-17
layout decision | AES |  | 2025-10-17 | Dependent on internal modeling results; selection needed before PRE can lock 10% redesign and pricing. | bar: 2025-10-17
Layout Redesign (PRE 10%, schedule, and binding pricing) | PRE | 2025-10-10 | 2025-11-21 | PRE to advance 10% layout + preliminary schedule + binding pricing. Must incorporate AES final layout choice, exhibit package, and clarification/ACE items. Assumes landowner feedback and geotech baseline are stable. | bar: 2025-10-17 to 2025-11-21
Updated PPA offer submission | AES |  | 2025-10-20 | Requires interim pricing basis for Google (510 vs. 550 option). AES submits updated offer in parallel with layout work; outcome informs contracting strategy. | bar: 2025-10-20
PPA decision | AES |  | 2025-10-31 | Google approval of updated offer; critical gating item. EPCA path only advances if PPA approved. | bar: 2025-10-31
EPCA negotiations | AES ↔ PRE | 2025-11-21 | 2025-12-15 | bar: 2025-11-24 to 2025-12-15
Earliest possible EPCA execution | AES ↔ PRE |  | 2025-12-15 | Requires: (i) PRE binding pricing and allowances log (Nov 21), (ii) true-up of any open ACE/tech spec deviations, (iii) completed exhibit set. Target aligns with PRE’s request to close EPCA by year-end. | bar: 2025-12-15

## Sheet2 (hidden)
Milestone / Deliverable | Owner | Start | Finish | Dependencies/Notes | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-20 | 2025-10-31 | 2025-11-21 | 2025-12-15
Project engineering document handoff | AES | 2025-10-03 | 2025-10-06 | What can be used from Redonda if anything?
AES provide external folder with EPCA exhibits | AES ↔ PRE |  | 2025-10-10 | Populate external drive with necessary exhibits; requires coordination with SMEs.
Internal layout modeling (510ac & 550ac) | AES | 2025-10-10 | 2025-10-17 | Modeling required to compare 510ac (2) GSU arrangement to 550ac (3) GSU arrangement. Output feeds layout decision.
layout decision | AES |  | 2025-10-17 | Dependent on internal modeling results; selection needed before PRE can lock 10% redesign and pricing.
Layout Redesign (PRE 10%, schedule, and binding pricing) | PRE | 2025-10-10 | 2025-11-21 | PRE to advance 10% layout + preliminary schedule + binding pricing. Must incorporate AES final layout choice, exhibit package, and clarification/ACE items. Assumes landowner feedback and geotech baseline are stable.
updated PPA offer submission | AES |  | 2025-10-20 | Requires interim pricing basis for Google (510 vs. 550 option). AES submits updated offer in parallel with layout work; outcome informs contracting strategy.
PPA decision | AES |  | 2025-10-31 | Google approval of updated offer; critical gating item. EPCA path only advances if PPA approved.
EPCA negotiations | AES ↔ PRE | 2025-11-21 | 2025-12-15
Earliest possible EPCA execution | AES ↔ PRE |  | 2025-12-15 | Requires: (i) PRE binding pricing and allowances log (Nov 21), (ii) true-up of any open ACE/tech spec deviations, (iii) completed exhibit set. Target aligns with PRE’s request to close EPCA by year-end.