## Sheet1
Assumptions & Exclusions Clarification Log
| Project | Crescent PV
| RFP Release Date | 2025-06-12
Procore Data Room Link
| EPC | Primoris | EPC Proposal Lead
EPC Proposal Lead Contact Email
No. | Proposal Section Reference | Assumption/Exclusion | AES Response if in agreement with statement in previous column, please state "Agreed" and include Name of Respondent/Date | EPC Response if in agreement with statement in previous column, please state "Agreed" and include Name of Respondent/Date | AES Response if in agreement with statement in previous column, please state "Agreed" and include Name of Respondent/Date | EPC Response if in agreement with statement in previous column, please state "Agreed" and include Name of Respondent/Date
1 |  |  | Discuss Domestic content/non-Domestic content inverter block blending. | Domestic content. Some of the modules are foreign and some are domestic. Split at the Inverter block level. AES to provide details on exact breakdown of modules and inverters that require domestic content.
2 | Civil Works | "Assumption - A12 - Primoris has assumed that the on-site water wells can be used for the dust mitigation purpose. Throughout the project duration, Primoris would require ~100 million gallons of water for backfill and dust control. Proposal assumes that the water can be purchased through the landowner at $0.50 per barrel of water. One barrel of water shall be defined as 37 gallons. We have assumed that there is at least one well in East and one in West parcel within the project boundary and each well produces ~100k gallons per day." | 100M gallons of water appears to be an unrealistically large volume. Please elaborate on water handling and storage strategy. | We will present the sheet that we put together. AES has seen in during Bellefield too. AES to help contact land owners to source water
3 | Civil Works | 3. Assume there will be no interference with Wind construction activites on the Access Roads included in the RUA. | The wind gen-tie will enter the solar construction area north of FM1763 (which is also the access road to the west solar area), and wind and solar gen-ties will run parallel/adjacent through a solar parcel up to the SY/SB. Please revise your bid to address potential access and schedule conflicts in this area, including any required coordination measures or cost impacts. | DOR for road maintenance/ repair AES to provide more details on direction of wind project construction access and timing
4 | Civil Works | Assumption - A13 - FM1763, CR 105S, and FM 2897S Roads are suitable for construction traffic and may be used for site access. Refer to the provided draft "Site Access Routes" for full breakdown of assumed lengths and maintenance plan. Price to be finalized with RUMA final approval. Primoris has also assumed there will be no other construction traffic on these roads during our construction schedule. | These are public county roads that may require upgrades or enhancements per the final RUMA, and they are likely to be used by other construction projects and existing wind farms during our construction period. Please revise your bid to account for potential road improvements and shared traffic conditions. | Discuss and determine how we will handle damages caused by multiple Contractors. PRE would like to know what path contractors will be taking when coming from the south. Travel up ROW for t-line?
5 | Solar PV Field Mechanical | 2. Price excludes Hail protection of the PV modules when in the pallet or installed on the tracker (60 degree HailPro). | Please provide a price add for hail protection of the PV modules when in the pallet and when installed on the tracker (60° HailPro). Final determination on inclusion will be made by the Engineering and Execution teams based on your quoted price. | Need manual from Module manufacturer to understand the procedures to follow for hail protection covers/ blankets, if any. AES to talk with insurance to see how we need to be covered pre installation. Builders risk policy may cover this.
6 | AC Electrical Systems | Assumption - A1 - PPS assumes ROW can be used as laydown area. | Please identify the specific ROW(s) you are referring to (e.g., public county roads, utility easements, or private leased corridors). Use of ROW for laydown is subject to lease terms, environmental and permitting restrictions, and AES approval, and may not be permissible. Laydown should be limited to areas designated in the approved Westwood 30% design unless otherwise directed by AES. Revise your bid accordingly to reflect permitted laydown areas only. | ROW being referenced is the north south one in image to right.
7 | Procurement | 1. Assume average module delivery rate of 30MW/week. | Please propose a range with upper and lower bounds. AES will evaluate with Vendor. | For 725MWdc layout - 20 to 35 MW per week. Starting lower and working the way up. AES to understand if there are manufacturer requirements on time between delivery to being on rack for warranty validity.
8 | Procurement | 2. Primoris is requesting 0.4% of total modules for construction spares. | Internal assumption is 5 spares per MW -0.27%. Confirm acceptance of 0.27% or justify the higher fraction. Provide pricing for both levels. | • We have seen higher module breakage on recent projects. • We can use 0.27/0.3 % in contract and can provide adder for remaining breakage. AES to provide module price.
9 | Procurement | The tracker design is using 60 degree stow which differs from the 30% Westwood design 75 degree. Domestic Content: 19.3 pts | This is lower DC product from Nextracker, need to align on pricing for intended product. Total DC points for tracker system = 28.7. Breakdown: Torque Tube – 11.0, Fasteners – 0.4, Slew Drive – 1.9, Dampers – 0.5, Motor – 2.8, Controller – 0.7, Rails – 2.0, Production – 9.4. All points must be DC-compliant as per AES sourcing strategy. | 28.7 points including the production bonus of 9.4 points consistent with Section 5, Updated Table for Solar PV Ground-Mount, referenced in notice 2025-08
10 | Contractor General | The tracker design is using 60 degree stow which differs from the 30% Westwood design 75 degree. Domestic Content: 19.3 pts | Work with Execution PM to determine how much scope we want to include
11 | Civil Works | 3. The proposal does not include any allowance for rock, slurry, or cased/shored excavation. We are assuming dry, stable earth excavation for completion of all excavation activities pending being provided a geotechnical report. | Do we need to consider rock in basin excavation? | No, per the preliminary Geotechnical report provided. We would like to confirm through supplemental geotech report.
12 | Civil Works | 2. Base bid proposal pricing (based on 30%) does not include cost for fiber roll, rock check dams, or diversion swales since the Westwood 30% drawings do not show these. | List any additional erosion and sediment control measures you reasonably expect beyond the Westwood 30% drawings and price them with unit rates and assumed quantities. Identify items already included versus alternates. | For 30% proposal submission, we used quantities from the civil package. We have included additional SWPPP/ BMP items in alternate design pricing.
14 | Civil Works | Not responsible for crop damage, livestock protection or drain tile repair/mitigation. | No drain tiles in irrigated portion, no crops in the field. May leave livestock as a risk. | AES to follow up to see if livestock just expected in beginning or throughout.
16 | Solar PV Field Mechanical | 3. Price excludes module washing during or after installation. | Need to include mod washing. | ~$4.4 million. Base price excludes module washing. This price is for 1 time mobilization and wash only and the exact timing of this activity is yet to be determined. AES and PRE to discuss this scope further.
17 | Solar PV Field Mechanical | 4. Scanning of each barcode on every module installed is excluded. | Check against B-1 req, also check with Tax to determine if required
18 | Solar PV Field Mechanical | 5. Double handling of modules is not included. | Confirm that double-handling as a result of contractor activities or schedule delay is included. | Confirmed. Double handling due to owner caused delays and things which are out of contractor's control are not included.
19 | AC Electrical Systems | 7. 750 kcmil cable length mentioned in the client's 30% design is 164,678 LNFT less than PRE's calculated value( three phase). Our analysis is that the client has not considered, the parallel run lengths in the calculation. | If this is in referecne to DC cable, the westwood 30% shows one way length in the 30% design.
20 | Contractor Testing & Commissioning | 2. Contractor guarantees that the Capacity Test output will be equal to or greater than 97% of the Expected Capacity in accordance with certain criteria as will be more precisely detailed in an exhibit to the EPC Contract (the “Guaranteed Capacity”), the terms of which shall be subject to negotiation by the parties prior to the execution of the EPC Contract. | AES to determine allowable guaranteed capacity
24 | AC Electrical Systems | Exclusion - E1 - PPS has not included any rock drilling in this proposal. | What is our internal assumption on transmission structure rock drilling?
25 | Estimating |  | Please provide a detailed list of “value plugs” currently included in your optimized layout proposal, including description, assumed quantity, and pricing basis, so AES can evaluate potential scope adjustments and compare the two proposals apples to apples. | We followed AES specs for alternate layout. Price optimization is based on optimized layout.
26 | Estimating |  | Please provide a detailed breakdown showing where technical specification deviations were priced in your proposal, including the basis for each deviation. | None.
27 | Estimating |  | Identify which of your deviations from AES’s technical specifications were made specifically to reduce cost, and provide the cost delta for each. | None.
28 | Estimating |  | risk category for trackers - was it 105mph or 114mph? | Risk category 2 which is 81mph for this region. AES engineers say risk category 2 is acceptable, however, 30% designs show 115mph for risk category 2.
29
30
31
32
33
34
35
36
37
38
39
40
41